## MVP Tracker
Bite — MVP Remaining Tasks
Last updated: Feb 11 2026 · Status: Pre-launch
# | Category | Task | Details / Notes | Priority | Status | Milestone | Est. Effort
FEATURES — CORE
1 | Features | Graceful "no captions" handling | When youtube_transcript_api fails, show friendly message: "This video doesn't have captions yet." Don't crash or show raw error. Blocks all testing. | Critical | Done | TestFlight | 0.5 day
2 | Features | Audio summaries (TTS) | Core value prop per brief. Integrate expo-speech or cloud TTS (ElevenLabs / Google). Add play/pause controls to summary screen. Commuter use case depends on this. | Critical | Not Started | App Store | 3-5 days
3 | Features | Offline reading mode | Cache summaries + refresher cards locally for offline access. AsyncStorage or SQLite. Important for commuters and spotty connections. | Critical | Not Started | App Store | 2-3 days
4 | Features | Push notifications | Integrate expo-notifications for: summary ready, new community content, refresher reminders. Request permission in onboarding/analyse flow. | High | Not Started | App Store | 2-3 days
5 | Features | Subscription tier enforcement (backend) | Paywall UI exists but no real gating. Implement usage limits per tier (Free: 3/mo, Pro: 30, Power: unlimited). Track credits in Supabase. Gate /summarise. | Critical | Done | App Store | 2-3 days
6 | Features | Payment integration (RevenueCat) | Paywall screen exists but no processor. Integrate RevenueCat for iOS in-app purchases + subscription management. Connect to tier enforcement. | Critical | Not Started | App Store | 3-5 days
7 | Features | Spaced repetition scheduling | Hooks exist (useDueCards) but no real algorithm. Implement SM-2 or simplified interval system for optimal refresher card timing. | Medium | Done | App Store | 1-2 days
MOCK DATA → REAL DATA
8 | Mock → Real | YouTube subscriptions import | Currently mocked (MOCK_YOUTUBE_SUBSCRIPTIONS). Integrate YouTube Data API v3 + OAuth to fetch user's actual subscriptions. | High | Not Started | App Store | 2-3 days
9 | Mock → Real | Channel latest videos | MOCK_CHANNEL_VIDEOS hardcoded per creator. Replace with YouTube Data API v3 search endpoint for real recent uploads. | High | Not Started | App Store | 1-2 days
10 | Mock → Real | Followers count on profile | Hardcoded followersCount = 0. Build real query from user_follows table in Supabase. Table exists — just need count query + hook. | Medium | Done | App Store | 0.5 day
11 | Mock → Real | Subscription status check in analyse.tsx | Uses summaries.length === 0 as proxy for "new user." Replace with actual tier status from subscriptions table. Ties into payment integration. | High | Done | App Store | 0.5 day
12 | Mock → Real | Home feed — real channel videos | Use real FEATURED_CREATORS channelId values to populate feed with actual unanalysed videos from user's preferred categories. | Medium | Not Started | App Store | 1-2 days
13 | Mock → Real | "Delete my data" flow | Currently shows a toast. Implement real deletion request — mailto: support@takeabite.ai at minimum. Ideally a backend endpoint. | Low | Done | App Store | 0.5 day
PROMPT CACHING & PERFORMANCE
14 | Performance | Enable Anthropic prompt caching | System prompt is large and identical per request. Add cache_control: {type: "ephemeral"} on system message. ~80% cost reduction on cache hits. Do this before testers start hammering the API. | High | Done | TestFlight | 0.5-1 day
15 | Performance | Cache system prompt + few-shot examples | Break Claude call into cached (system prompt, format instructions, examples) vs dynamic (transcript, preferences) blocks for max cache hit rate. | High | Done | TestFlight | 0.5 day
16 | Performance | Translation prompt caching | Translation calls also reuse a system prompt. Apply same caching strategy. Stacks with existing DB-level translation cache. | Medium | Done | App Store | 0.5 day
17 | Performance | React Query stale time tuning | Review query hooks — some may refetch too aggressively. Set appropriate staleTime (preferences: 5min, community: 1min, user summaries: 30s). | Low | Done | App Store | 0.5 day
18 | Performance | Image / thumbnail caching | YouTube thumbnails reload every render. Use expo-image or react-native-fast-image for disk caching across the app. | Medium | Done | App Store | 0.5-1 day
UI IMPROVEMENTS
19 | UI | Onboarding slides — new copy | Replace SLIDES array in welcome.tsx with new value props (watch later guilt, quality summaries, community, time reclaimed). First impression for testers. | Medium | Not Started | TestFlight | 0.5 day
20 | UI | Sign up — "Display name" placeholder | Change placeholder from "Full name" to "Display name" in register.tsx. One-line change. | Low | Not Started | TestFlight | 5 min
21 | UI | Confirm email screen | Create app/(auth)/confirm-email.tsx. Redirect after email signup instead of /. Without this, signup flow is broken/confusing. Full spec in UX doc. | High | Not Started | TestFlight | 0.5 day
22 | UI | Analyse screen — loading state fix | Preview info competes with loader for space. Move preview to top, center loader below. Add "Allow Notifications" button. Currently confusing for testers. | Medium | Not Started | TestFlight | 0.5-1 day
23 | UI | Home screen redesign — mixed feed | Replace section-based layout with single mixed vertical feed. Interleave community summaries, refresher cards, personalise prompt. Major index.tsx refactor. | High | Not Started | App Store | 2-3 days
24 | UI | Personalise flow — 2-step redesign | Replace 3-step (interests → goals → categories) with 2-step (main categories → subcategories). New subcategory chips per category. | Medium | Not Started | App Store | 1-2 days
25 | UI | Explore screen redesign | Custom header (+, title, search icon), full-width thumbnails, 2x2 creator grid, remove CategoryGrid. Major explore.tsx refactor. | High | Not Started | App Store | 2-3 days
26 | UI | Profile screen redesign | Combine stats into one line, 2-tab switcher (Summaries / Saved), remove Settings link, large thumbnails. | Medium | Not Started | App Store | 1-2 days
27 | UI | Summary detail — action CTAs | Add YouTube-style action row (Translate, Like, Save, Share, Report) between title block and channel info. New likeStore needed. | Medium | Not Started | App Store | 1 day
28 | UI | Summary detail — section navigator scroll | SectionNavigator should reappear on scroll-up. Track scroll direction with onScroll and Animated.View translateY. | Low | Not Started | App Store | 0.5 day
29 | UI | Summary detail — refresher cards section | Replace lonely CTA button with stacked cards visual + count + "Review" button per UX spec 8.6. | Low | Not Started | App Store | 0.5 day
30 | UI | Section actions — Play button + rename | Add "Play" action (opens YouTube at timestamp). Rename "Bookmark" → "Save". Pass videoId + timestampStart as props. | Low | Not Started | App Store | 0.5 day
31 | UI | Analyse screen — Import from Google mock | Add "Import from Google" button below URL input. Shows toast "Coming soon" for now. | Low | Not Started | App Store | 15 min
32 | UI | Settings screen — minor cleanups | Rename "Summary Language" → "Primary summary language". Merge Legal + About → "Other". Update delete data flow. | Low | Not Started | App Store | 0.5 day
33 | UI | Category constant update | Update CATEGORIES in types/summary.ts to 12 new categories. Add mapping utility for old → new. Don't break existing data. | Medium | Not Started | App Store | 0.5 day
34 | UI | Dark mode support | No dark mode constants yet. Add Colors.dark object + toggle in settings. iOS users expect this. | Low | Not Started | App Store | 2-3 days
SOCIALS & MARKETING
35 | Socials | Create Twitter/X app account | Set up @takeabiteai or similar. Pin origin story. Bio: "Your YouTube backlog, summarised." Start before TestFlight so testers can follow. | High | Not Started | TestFlight | 1 hour
36 | Socials | Create Twitter/X personal (founder) | Start build-in-public posting. Pin the "400 videos in Watch Later" hook tweet per social media plan. | High | Not Started | TestFlight | 1 hour
37 | Socials | Create LinkedIn app page | Company page for Bite / Take a Bite AI. Professional branding, summaries as thought leadership. | High | Not Started | App Store | 1 hour
38 | Socials | LinkedIn personal — start posting | Founder-led build-in-public posts 3-5x/week. Share learnings, behind-the-scenes, early traction. | High | Not Started | App Store | Ongoing
39 | Socials | Indie Hackers profile + first post | Create product page. Write first "building in public" journal entry about the problem. | Medium | Not Started | App Store | 1-2 hours
40 | Socials | Landing page (takeabite.ai) | Web page for waitlist / early access. Email capture, value prop, screenshots. Simple Next.js or Framer. | High | Not Started | App Store | 1-2 days
41 | Socials | App Store assets preparation | Screenshots (6.7" + 6.5"), description, keywords, privacy policy URL, support URL. Required for submission. | Critical | Not Started | App Store | 1-2 days
42 | Socials | Privacy Policy & Terms of Service | Legal pages for App Store + Settings links. Use a generator + customize. Host on takeabite.ai. | Critical | Not Started | App Store | 0.5-1 day
OPERATIONAL
43 | Ops | TestFlight beta setup | Configure Expo EAS Build for iOS. Create TestFlight internal testing group. Invite 10-20 friends & family. | Critical | Not Started | TestFlight | 1 day
44 | Ops | Server deployment | Express server runs locally on port 3000. Deploy to Railway / Render / Fly.io. Update mobile app to point to production URL. Testers need a live backend. | Critical | Not Started | TestFlight | 0.5-1 day
45 | Ops | Environment variable audit | Verify .env not committed to git. Check .gitignore. Review Supabase RLS policies. Security baseline before any external access. | High | Done | TestFlight | 0.5 day
46 | Ops | Error monitoring (Sentry) | Add Sentry or Bugsnag for crash reporting. Critical for seeing what breaks during beta testing. | High | Not Started | TestFlight | 0.5 day
47 | Ops | Support email setup | Set up support@takeabite.ai. Needed for App Store, data deletion, user feedback. Simple forwarder to start. | High | Not Started | TestFlight | 1 hour
48 | Ops | App Store submission prep | Apple Developer account, bundle ID verified, review guidelines compliance, age rating, content description. | Critical | Not Started | App Store | 1 day
49 | Ops | Analytics integration | Add Mixpanel, PostHog, or Amplitude. Track: summary generated, onboarding completed, paywall viewed, tier selected, share tapped. | High | Not Started | App Store | 1 day
50 | Ops | Rate limiting on server | No rate limiting on Express. Add express-rate-limit on /summarise and /translate. Critical once public to prevent abuse. | High | Done | App Store | 0.5 day
51 | Ops | Database backup strategy | Enable Supabase automatic backups (Pro plan). Verify RLS policies don't leak data between users. | Medium | Not Started | App Store | 0.5 day
52 | Ops | CI/CD pipeline | EAS Build + EAS Submit for automated iOS builds. GitHub Actions for server. Saves time on repeat submissions. | Medium | Not Started | App Store | 1 day

## Summary
MVP Task Summary
By Milestone
Milestone | Tasks | What it means
TestFlight | 14 | Minimum bar to ship to friends & family for real feedback
App Store | 38 | Everything needed for public launch — payments, polish, marketing, compliance
By Category
Category | Total | TestFlight | App Store
Features | 7 | 1 | 6
Mock → Real | 6 | 0 | 6
Performance | 5 | 2 | 3
UI | 16 | 4 | 12
Socials | 8 | 2 | 6
Ops | 10 | 5 | 5
TOTAL
TestFlight Checklist — Ship This First
☑ | When youtube_transcript_api fails, show friendly message: "This video doesn't have captions yet." Don't crash or show raw error. Blocks all testing. | Graceful "no captions" handling
☑ | System prompt is large and identical per request. Add cache_control: {type: "ephemeral"} on system message. ~80% cost reduction on cache hits. Do this before testers start hammering the API. | Enable Anthropic prompt caching
☑ | Break Claude call into cached (system prompt, format instructions, examples) vs dynamic (transcript, preferences) blocks for max cache hit rate. | Cache system prompt + few-shot examples
☐ | Replace SLIDES array in welcome.tsx with new value props (watch later guilt, quality summaries, community, time reclaimed). First impression for testers. | Onboarding slides — new copy
☐ | Change placeholder from "Full name" to "Display name" in register.tsx. One-line change. | Sign up — "Display name" placeholder
☐ | Create app/(auth)/confirm-email.tsx. Redirect after email signup instead of /. Without this, signup flow is broken/confusing. Full spec in UX doc. | Confirm email screen
☐ | Preview info competes with loader for space. Move preview to top, center loader below. Add "Allow Notifications" button. Currently confusing for testers. | Analyse screen — loading state fix
☐ | Set up @takeabiteai or similar. Pin origin story. Bio: "Your YouTube backlog, summarised." Start before TestFlight so testers can follow. | Create Twitter/X app account
☐ | Start build-in-public posting. Pin the "400 videos in Watch Later" hook tweet per social media plan. | Create Twitter/X personal (founder)
☐ | Configure Expo EAS Build for iOS. Create TestFlight internal testing group. Invite 10-20 friends & family. | TestFlight beta setup
☐ | Express server runs locally on port 3000. Deploy to Railway / Render / Fly.io. Update mobile app to point to production URL. Testers need a live backend. | Server deployment
☑ | Verify .env not committed to git. Check .gitignore. Review Supabase RLS policies. Security baseline before any external access. | Environment variable audit
☐ | Add Sentry or Bugsnag for crash reporting. Critical for seeing what breaks during beta testing. | Error monitoring (Sentry)
☐ | Set up support@takeabite.ai. Needed for App Store, data deletion, user feedback. Simple forwarder to start. | Support email setup
Priority Legend |  | Status Legend
Critical |  | Not Started
High |  | In Progress
Medium |  | Done
Low |  | Blocked